## ACTIVE SHEET
PROGRAM, PROJECT OR EVENT 1) NATIONAL 2) CLUB 3) REGIONAL | Spring - Summer | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG
| 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | Convention | High Holiday PREP
Membership Campaign | Plan & Budget | JUL: Chair & committee in place; AUG: Plan Membership Campaign; SEP: Publicize - Rabbi's Letter to Schools; OCT: Distribute Club Calendar at HH; FEB: Have Fun, Invitations, Membership Applications and Dues Collections
World Wide Wrap & Build a Pair | Plan & Budget | AUG: Chair & committee in place; SEP: Start BAP Planning & purchase; OCT: Start WWW Planning. Register Online; NOV: Purchase Extra Tefillin; DEC: Kids Build a Pair in Schools; JAN: Publicize - Send Letter from Rabbi; FEB: WWWrap; MAR: Follow up Story
Yellow Candles | Plan & Budget |  | Chair & committee in place | Begin YC Planning | YC Planning | YC plan & purchase | YC plan & purchase | Begin YC Publicity | YC Publicize -Send Letter from Rabbi | YC Pack, Distribute & Publicize | YC Distribute - Yom HaShoah Program | Collect donations | Collect donations / Write Follow up Story / Plan
Men's Club Shabbat | Plan & Budget Set MC Shabbat Date(s) | AUG: Chair & committee in place; DEC: Plan format with Rabbi. Register Online; JAN: Assign Roles; MAR: Celebrate Shabbat; APR: Follow up Story/Plan
FJMC Convention | Plan & Budget |  | Chair & committee in place |  |  |  | Begin Convention Registration | Continue Convention Registration | Begin a Tribute Journal Campaign | Begin a Tribute Journal Campaign | Run First Time Orientation Dinners | Plan Coverage of All Programs | Pack Bags / Finalize Your Presentations | TORONTO CONVENTION
Shomrei Ha'aretz - Environment | Plan & Budget |  | Chair & committee in place | Plan Year Long Environmental Programs | Publicize Year Environmental Programs | SHA Environment Program #1 | Write Follow Up Story - Plan TuBishvat #2 | Publicize SHA TuBishvat Program #2 | SHA TuBishvat Program #2 | Write Follow Up Story - Plan Compost #3 | Publicize SHA Composting Program #3 | SHA Composting Program #3 | Write Follow Up Story in Newspaper
Hearing Men's Voices | Plan & Budget | AUG: Chair & committee in place; SEP: Plan format, topics, dates, etc.; OCT: Begin Publicity for Year's HMV Events; NOV: HMV Event #1; JAN: HMV Event #2; MAR: HMV Event #3; MAY: HMV Event #4
Family Financial Conversation (Was: Family Financial Educaiton; Health, Weatth & Retirement) | Plan & Budget | AUG: Chair & committee in place; OCT: Plan format, topics, dates, etc.; NOV: Begin Publicity for Year's HWR Events; DEC: H,W,R Event #1; MAR: Publicize H,W,R Event #2; APR: H,W,R Event #2; MAY: Write Follow Up Story in Newspaper
Yad Shel Chai - Post B'nai Mitzvah Torah Readings | Plan & Budget | JUL: Chair & committee in place; AUG: Yad Shel Chai Purchase; SEP: YSC Intro Program in Schools; OCT: Purchase Yads for Readers; FEB: Yad Shel Chai - Post B'nai Mitzvah Torah Readings All Year Round; JUN: Write Follow Up Story in Newspaper
Quality Club Awards | Plan next year's activities using QCA online qualifications | AUG: Chair & committee in place; NOV: Check Website for Due Date, etc.; MAY: Check Website for Due Date, etc.; JUL: Receive Award at Convention; AUG: Note: Quality Club Awards in even years may be distributed at Regional Events
Torch Awards | Plan & Budget | AUG: Chair & committee in place; SEP: Document, Photo & Video Tape Club Programs for Torch Award Submissions; MAY: Torch Award Submission Deadline
Club Inititives - Enter into Calender Your Dates for Planning, Publicity, Initiatives, Write Follow up News Stories, Evaluation. Add Rows if Needed for Additional Initiatives; Add Columns to Start Planning for Next Year.
Club Initiative #1 | Plan & Budget | AUG: Chair & committee in place
Club Initiative #2 | Plan & Budget | AUG: Chair & committee in place
Club Inititives - Enter into Calender Your Region's Dates for Planning, Publicity, Initiatives, Write Follow up News Stories, Evaluation. Add Rows if Needed for Additional Initiatives; Add Columns to Start Planning for Next Year.
Regional Retreat | Plan dates, budgets, formats, etc. | JUL: Begin to Publicize Dates and Initiatives; AUG: Chair & committee in place
Local Training | Plan dates, budgets, formats, etc. | JUL: Begin to Publicize Dates and Initiatives; AUG: Chair & committee in place
Regional Initiatives | Plan dates, budgets, formats, etc. | JUL: Begin to Publicize Dates and Initiatives; AUG: Chair & committee in place