## Advanced Planning
Etz Chaim 1711 Holocaust Garden Renewal - Program Advanced Planning
Task | Committee | Assignee | Assistant | Due Date | Status
Develop renovation design | Holocaust Garden Renewal | Alan Struletz |  | 2011-04-30 | Complete
Write proposal for shul board | Holocaust Garden Renewal | Barry Riesenberg |  | 2011-12-31 | Complete
Present proposal to shul board and secure approval | Holocaust Garden Renewal | Jeff Frankel |  | 2012-01-15 | Complete
Install Garden renovations and landscaping | Holocaust Garden Renewal | Alan Struletz / Outdoor Expressions |  | 2012-08-31 | Complete
Create brick order form and publicity materials | Holocaust Garden Renewal | Barry Riesenberg | Steve Krodman | 2012-11-10 | Complete
Create brick certificate template | Holocaust Garden Renewal | Steve Krodman |  | 2012-11-10 | Complete
Print brick certificates as required | Holocaust Garden Renewal | Barry Riesenberg |  | Ongoing | Ongoing
Manage commemorative brick / bench sales | Holocaust Garden Renewal | Barry Riesenberg |  | Ongoing | Ongoing
Track project expenses and revenues | Holocaust Garden Renewal | Paul Wachter |  | Ongoing | Ongoing
.

## Sample
Sample Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
Update email list for latest committee (remove old members) |  | Jim |  | 3.1.2013 | Done
Add new committee member or two |  | Robert | Brian | 3.1.2013 | Done
Create budget | Finance | Bruce |  |  | Done
Speaker Topics | Speakers | Joe | Jim | 3.15.2013 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 3.15.2013 | Done
Update website |  | Jacob |  | 3.1.2013 | Done
Produce Brochure | Publicity | Josh | Jim | 3.25.2013 | Done
Create press releases; articles | Publicity | Josh | Jim | 4.10.2013 | Done
Email Press Releases to newspapers |  | Josh |  | 4.15.2013 | Done
Update menus | Commisary | Jim |  | 4.25.2013 | Done
Get photographer |  | Joe |  | 4.30.2013 | Done
Phone-a-thon |  | Robert | Brian | 2.29.2013 | Open
Book Room |  | Bruce |  | 3.1.2013 | Done
Lessons Learned Meeting |  | all |  | 6.15.2013
Birkat booklets: Mark Druy |  | Elliot
Greeters Greg Kadinov |  | David
Buy Insurance |  | David
Camp staff person doing a greeting |  | Elliot | yes
People to Introduce speakers |  | Both
Cameraman for group pictures |  | David
Rent chairs for Sanctuary |  | Elliot | Lou
Schedule HMV sessions |  | Both
Recruit HMV facilitator |  | Both
Talk to Committee about where to hold sessions |  | Both
Compile survey |  | Both