## Advanced Planning
Etz Chaim 1711 Walking G-d's Paths - Program Advanced Planning
Task | Committee | Assignee | Assistant | Due Date | Status
Initial discussions with Fr. Ray | Interfaith Dialogue | Steve Dix |  | 1Q 2012 | Complete
Invite St. Ann's group to attend Men's Club Shabbat services 4/14/12 | Interfaith Dialogue | Barry Riesenberg | Steve Dix | 2012-03-15 | Complete
Develop plan for pilot program | Interfaith Dialogue | Barry Riesenberg | Steve Dix | 2012-04-30 | Complete
Invite participants | Interfaith Dialogue | Barry Riesenberg | Steve Dix | 2012-05-15 | Complete
Session 1 | Interfaith Dialogue | Barry Riesenberg | Steve Dix | 2012-06-25 | Complete
Attend Farewell Mass for Fr. Ray | Interfaith Dialogue | Barry Riesenberg | Steve Dix, Steve Krodman | 2012-07-01 | Complete
Session 2 | Interfaith Dialogue | Barry Riesenberg | Steve Dix | 2012-07-30 | Complete
Session 3 | Interfaith Dialogue | Barry Riesenberg | Steve Dix | 2012-08-27 | Complete
Session 4 | Interfaith Dialogue | Barry Riesenberg | Steve Dix | 2012-09-24 | Complete
Session 5 | Interfaith Dialogue | Barry Riesenberg | Steve Dix | 2012-10-29 | Complete
Session 6 | Interfaith Dialogue | Barry Riesenberg | Steve Dix | 2012-11-26 | Complete
Interfaith Christmas-Chanukah Dinner | Interfaith Dialogue | All |  | 2012-12-15 | Complete
.

## Sample
Sample Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
Update email list for latest committee (remove old members) |  | Jim |  | 3.1.2013 | Done
Add new committee member or two |  | Robert | Brian | 3.1.2013 | Done
Create budget | Finance | Bruce |  |  | Done
Speaker Topics | Speakers | Joe | Jim | 3.15.2013 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 3.15.2013 | Done
Update website |  | Jacob |  | 3.1.2013 | Done
Produce Brochure | Publicity | Josh | Jim | 3.25.2013 | Done
Create press releases; articles | Publicity | Josh | Jim | 4.10.2013 | Done
Email Press Releases to newspapers |  | Josh |  | 4.15.2013 | Done
Update menus | Commisary | Jim |  | 4.25.2013 | Done
Get photographer |  | Joe |  | 4.30.2013 | Done
Phone-a-thon |  | Robert | Brian | 2.29.2013 | Open
Book Room |  | Bruce |  | 3.1.2013 | Done
Lessons Learned Meeting |  | all |  | 6.15.2013
Birkat booklets: Mark Druy |  | Elliot
Greeters Greg Kadinov |  | David
Buy Insurance |  | David
Camp staff person doing a greeting |  | Elliot | yes
People to Introduce speakers |  | Both
Cameraman for group pictures |  | David
Rent chairs for Sanctuary |  | Elliot | Lou
Schedule HMV sessions |  | Both
Recruit HMV facilitator |  | Both
Talk to Committee about where to hold sessions |  | Both
Compile survey |  | Both