## Advanced Planning
Taste of Steak, Scotch and Talmud in the Sukkah Program Advanced Planning
Date | 2012-10-06
Task | Committee | Assignee | Assistant | Due Date | Status
Identify Program Lead | Men's Club Programming Chair | Bob Olshan | Jim Singman | August prior year (Event on 33rd day of Omer) | done
Schedule Event (Check synagogue & community calendars) | Program Lead | Bob Olshan | Jim Singman | August prior year (Event on 33rd day of Omer) | done
Coordinate with Rabbi, Hazzan, Sunday School, USY, Israel Committee | Program Lead | Bob Olshan | Jim Singman | three months prior | done
Find volunteers to lead: Meal, Scotch Tasting, Talmud and Publicity | Program Lead | Bob Olshan | Jim Singman | two months prior | done
Create Budget and update as needed | Program Lead | Bob Olshan | Jim Singman | two months prior | done
Scotch Tasting Planning | Entertainment | Michael Waxenberg | Michael Shanas | two months prior | done
Taste of Talmud Planning | Entertainment | Rabbi Dr. Ryan Dulkan |  | one month prior | done
Create Publicity Flyer & upload to website | Publicity | Gary Kodner | Bob Olshan | two months prior | done
Publicize in Local Papers, Synagogue Bulletin Men's Club Article | Publicity | Gary Kodner | Bob Olshan | one month prior | done
Publicize in E-mail Blast, Shabbat Bulletin, Send E-mail out to Men's club | Publicity | Gary Kodner | Bob Olshan | two weeks prior | done
Please RSVP to the ofﬁce ASAP - before so we can order | Publicity | Gary Kodner | Bob Olshan | two weeks prior
the steaks). | Meal | Jim Singman | Don Pearline | one month prior | done
Purchase Food | Meal | Jim Singman | Don Pearline | during week prior | done
Prepare Food (Steak & Sides) | Meal | Jim Singman | Don Pearline | day of event | done
Organize Food Ticket Sales | Meal & Finance Lead | Jim Singman | Don Pearline | day of event | done
Article with pictures in Newsletter | Program Lead or president | Bob Olshan | Gary Kodner | prior to next synagogue newsletter | done
Lessons Learned | Program Chair & Program Lead | Bob Olshan | Jim Singman | Next Men's Club BOD mtg | done
.

## Sample
Sample Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
Update email list for latest committee (remove old members) |  | Jim |  | 3.1.2013 | Done
Add new committee member or two |  | Robert | Brian | 3.1.2013 | Done
Create budget | Finance | Bruce |  |  | Done
Speaker Topics | Speakers | Joe | Jim | 3.15.2013 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 3.15.2013 | Done
Update website |  | Jacob |  | 3.1.2013 | Done
Produce Brochure | Publicity | Josh | Jim | 3.25.2013 | Done
Create press releases; articles | Publicity | Josh | Jim | 4.10.2013 | Done
Email Press Releases to newspapers |  | Josh |  | 4.15.2013 | Done
Update menus | Commisary | Jim |  | 4.25.2013 | Done
Get photographer |  | Joe |  | 4.30.2013 | Done
Phone-a-thon |  | Robert | Brian | 2.29.2013 | Open
Book Room |  | Bruce |  | 3.1.2013 | Done
Lessons Learned Meeting |  | all |  | 6.15.2013
Birkat booklets: Mark Druy |  | Elliot
Greeters Greg Kadinov |  | David
Buy Insurance |  | David
Camp staff person doing a greeting |  | Elliot | yes
People to Introduce speakers |  | Both
Cameraman for group pictures |  | David
Rent chairs for Sanctuary |  | Elliot | Lou
Schedule HMV sessions |  | Both
Recruit HMV facilitator |  | Both
Talk to Committee about where to hold sessions |  | Both
Compile survey |  | Both