## Sheet1
Program Advanced Planning - Best Overall Activities
Summary | Each activity has its own characteristics with variations in the advanced planning required. What follows is a general description of how our Men's Club typically will plan for a particular activity. Some activities require signficiantly more advanced planning while others require very little.
When | Description
Spring prior to following programming year. | (A) Working together with the Men's Club board, identify activities we plan to have in following year. As a starting point, we assume that we'll have the same activities, other than some specific programs that did not generate much interest.
(B) Determine dates for all activities. We start out with the various holidays, as many of our programs specific to certain holidays. We look at the religious school calender as some of our programs involve the religious school. We also try to have our 9 breakfast programs on dates when the religious school is in session, as that's when many people are in our syngague on a Sunday morning. We find out when the cantor plans to have his major concerts, as the Men's Club often will sponsor the dinner prior to the concert.
(C) Meeting with the Programming Director. This is a meeting held 3 times per year where representatives from the various programming arms and committees of the synagogue meet to discuss our upcoming plans. This provides an opportunity to look for ways to collaborate on programs as well as identify in advance any potential conflicts in scheduling.
(D) Throughout the following year, change dates as needed. Sometimes add programs - for example, an arm of the synagogue wants to collaborate with the Men's Club for an event or we hear of a great movie to show that would generate a lot of interest.
Activity confirmed | Be sure it's calendared with a room reserved at the synagogue.
Several weeks or months prior to program | If it's a major event (eg, Distintinguished Service Award banquet or one involving mutliple groups of people), start planning. Have initial meeting with game plan including timeline for planning, roles and responsibilities, etc.
Details are finalized, preferably at least 2 months prior. | Complete program flyer and submit to temple with the following information:
(1) Date and time of program
(2) Sponsorship (eg, Men's Club, sometimes with other groups)
(3) Name of Program and/or Speaker
(4) Description of program, sometimes including a brief bio of speaker
(5) Cost of program which may vary by Men's Club members vs non-members, as well as RSVP in advance vs walk-ins.
(6) RSVP / contact information
1-2 months in advance or earlier | Submit online publicity form for internal and external publicity (Dave Diamond)
At least one month in advance to program date | Temple-wide publicity: announcement of program on Shabbat leaflets, program flyer around shul, standalone e-blasts about program, inclusion in weekly program announcements.
1-2 weeks prior to program | Secure Men's Club volunteers (4-6) on event date: pick-up all food/drinks and supplies, cook as needed, set-up food, handle registration, verify room logistics, greet and introduce speaker, etc.
3 days prior to program | Expected number of attendees based on RSVPs to date and anticipated walk-ins
3 days prior to program | Submit room function form - Set-up for seating (tables + chairs), registration table, and tables for food and drinks, podium/mic if needed, and any audio-visual needs -TV, screen, projector, laptop, etc. (Dave Diamond)
3 days prior to program | Arranage for all food, drinks, paper goods
Shortly after program | Work with Treasurer and Assistant Treasurer in determining all program revenues and expenses.
Next Men's Club Board meeting | Discuss program, lessons learned, etc.