## Advanced Planning
Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
.

## Sample
Program Advanced Planning - Israel Inside: How a Small Nation Makes a Big Difference, Discussion
Date | Description
5/2/12 | Approached by member (Lisa Roland) of temple's Israel Engagement Committee to partner with Men's Club at a breakfast program, and show the movie "Israel Inside".
2012-05-15 | Secured November program date with temple programming director. (Dave Diamond)
Next few months | Communications with Lisa Roland on program logistics, including speakers.
Sept. 2012 | Submit online publicity form for internal and external publicity (Dave Diamond)
Sept. 2012 | Complete program flyer and submit to temple (Dave Diamond)
Oct / Nov. 2012 | Temple-wide publicity: announcement of program on Shabbat leaflets, program flyer around shul, standalone e-blasts about program, inclusion in weekly program announcements.
1-2 weeks prior to program | Secure Men's Club volunteers (4-6) on event date: pick-up all food/drinks and supplies, cook eggs, set-up food, handle registration, verify room logistics, greet and introduce speaker, etc.
3 days prior to program | Expected number of attendees based on RSVPs to date and anticipated walk-ins (Joe Springut)
3 days prior to program | Submit room function form - Set-up for seating (tables + chairs), registration table, and tables for food and drinks, podium/mic if needed, and any audio-visual needs -TV, screen, projector, laptop, etc. (Dave Diamond)
3 days prior to program | Arranage for all food, drinks, paper goods (Joe Springut)
Shortly after program | Work with Treasurer and Assistant Treasurer in determining all program revenues and expenses.